## Sheet3
| 2019-06-10 | 2019-06-17 | 2019-06-24 | 2019-07-01 | 2019-07-08 | 2019-07-15 | 2019-07-22 | 2019-07-29
Controller Methods
Empty Pages
Page Design
Controller Methods Implementations
Services Class
Services Methods
Services Methods Implementations
Android
Htet Aung Lin
Chit Thae
Soe Yadanar Tun
Ei Phyu Phyu Thant
Htet Eaindray Hlaing
Hmu Pyae Shan
Win Theingi
Zaw Min Lwin
Myat Lin
Issac

## Schedule
ID | Category | Role | Task | Duty | Date From | Date To | Status | Remark
1 | Controller Methods | Anonymous | ClinicController.java | Htet Aung Lin | 2019-06-11 | 2019-06-11
2 | Controller Methods | Anonymous | PublicDoctorController.java | Chit Thae | 2019-06-11 | 2019-06-11
3 | Controller Methods | Anonymous | HomeController.java | Zaw Min Lwin | 2019-06-11 | 2019-06-11 | Complete
4 | Controller Methods | Anonymous | SignUpController.java | Zaw Min Lwin | 2019-06-11 | 2019-06-11 | Complete
5 | Controller Methods | Member | MemberBookingController.java | Soe Yadanar Tun | 2019-06-11 | 2019-06-11
6 | Controller Methods | Member | FamilyMemberController.java | Ei Phyu Phyu Thant | 2019-06-11 | 2019-06-11
7 | Controller Methods | Partner | BookingController.java | Htet Eaindray Hlaing | 2019-06-11 | 2019-06-11
8 | Controller Methods | Partner | ClinicController.java | Hmu Pyae Shan | 2019-06-11 | 2019-06-11
9 | Controller Methods | Partner | DoctorController.java | Win Theingi | 2019-06-11 | 2019-06-11
10 | Controller Methods | Partner | PatientController.java | Htet Aung Lin | 2019-06-11 | 2019-06-11 | Complete
11 | Controller Methods | Partner | TimeTableController.java | Zaw Min Lwin | 2019-06-11 | 2019-06-11 | Complete
12 | Empty Pages | Anonymous | ClinicController.java | Htet Aung Lin | 2019-06-11 | 2019-06-11
13 | Empty Pages | Anonymous | PublicDoctorController.java | Chit Thae | 2019-06-11 | 2019-06-11
14 | Empty Pages | Anonymous | HomeController.java | Zaw Min Lwin | 2019-06-11 | 2019-06-11 | Complete
15 | Empty Pages | Anonymous | SignUpController.java | Zaw Min Lwin | 2019-06-11 | 2019-06-11 | Complete
16 | Empty Pages | Member | MemberBookingController.java | Soe Yadanar Tun | 2019-06-11 | 2019-06-11
17 | Empty Pages | Member | FamilyMemberController.java | Ei Phyu Phyu Thant | 2019-06-11 | 2019-06-11
18 | Empty Pages | Partner | BookingController.java | Htet Eaindray Hlaing | 2019-06-11 | 2019-06-11
19 | Empty Pages | Partner | ClinicController.java | Hmu Pyae Shan | 2019-06-11 | 2019-06-11
20 | Empty Pages | Partner | DoctorController.java | Win Theingi | 2019-06-11 | 2019-06-11
21 | Empty Pages | Partner | PatientController.java | Htet Aung Lin | 2019-06-11 | 2019-06-11 | Complete
22 | Empty Pages | Partner | TimeTableController.java | Zaw Min Lwin | 2019-06-11 | 2019-06-11 | Complete
23 | Page Design | Anonymous | clinics.html
24 | Page Design | Anonymous | doctor.html
25 | Page Design | Anonymous | doctors.html
26 | Page Design | Anonymous | index.html
27 | Page Design | Anonymous | login.html
28 | Page Design | Anonymous | schedules.html
29 | Page Design | Anonymous | signup.html
30 | Page Design | Member | booking.html
31 | Page Design | Member | bookings.html
32 | Page Design | Member | create-family.html
33 | Page Design | Member | family.html
34 | Page Design | Member | familyMemberCreate.html
35 | Page Design | Member | familyMemberUpdate.html
36 | Page Design | Member | home.html
37 |  | Partner
38
39
40
41
42
43
44
45
46
Formulas:
Date To = [Date From]