## Sheet3
| 2019-06-10 | 2019-06-17 | 2019-06-24 | 2019-07-01 | 2019-07-08 | 2019-07-15 | 2019-07-22 | 2019-07-29
Controller Methods
Empty Pages
Page Design
Controller Methods Implementations
Services Class
Services Methods
Services Methods Implementations
Android
Htet Aung Lin
Chit Thae
Soe Yadanar Tun
Ei Phyu Phyu Thant
Htet Eaindray Hlaing
Hmu Pyae Shan
Win Theingi
Zaw Min Lwin
Myat Lin
Issac

## Schedule
ID | Category | Role | Task | Duty | Date From | Date To | Status | Remark
1 | Controller Methods | Anonymous | ClinicController.java | Htet Aung Lin | 2019-06-11 | 2019-06-11
2 | Controller Methods | Anonymous | PublicDoctorController.java | Chit Thae | 2019-06-11 | 2019-06-11
3 | Controller Methods | Anonymous | HomeController.java | Zaw Min Lwin | 2019-06-11 | 2019-06-11 | Complete
4 | Controller Methods | Anonymous | SignUpController.java | Zaw Min Lwin | 2019-06-11 | 2019-06-11 | Complete
5 | Controller Methods | Member | MemberBookingController.java | Soe Yadanar Tun | 2019-06-11 | 2019-06-11
6 | Controller Methods | Member | FamilyMemberController.java | Ei Phyu Phyu Thant | 2019-06-11 | 2019-06-11
7 | Controller Methods | Partner | BookingController.java | Htet Eaindray Hlaing | 2019-06-11 | 2019-06-11
8 | Controller Methods | Partner | ClinicController.java | Hmu Pyae Shan | 2019-06-11 | 2019-06-11
9 | Controller Methods | Partner | DoctorController.java | Win Theingi | 2019-06-11 | 2019-06-11
10 | Controller Methods | Partner | PatientController.java | Htet Aung Lin | 2019-06-11 | 2019-06-11 | Complete
11 | Controller Methods | Partner | TimeTableController.java | Zaw Min Lwin | 2019-06-11 | 2019-06-11 | Complete
12 | Empty Pages | Anonymous | ClinicController.java | Htet Aung Lin | 2019-06-11 | 2019-06-11
13 | Empty Pages | Anonymous | PublicDoctorController.java | Chit Thae | 2019-06-11 | 2019-06-11
14 | Empty Pages | Anonymous | HomeController.java | Zaw Min Lwin | 2019-06-11 | 2019-06-11 | Complete
15 | Empty Pages | Anonymous | SignUpController.java | Zaw Min Lwin | 2019-06-11 | 2019-06-11 | Complete
16 | Empty Pages | Member | MemberBookingController.java | Soe Yadanar Tun | 2019-06-11 | 2019-06-11
17 | Empty Pages | Member | FamilyMemberController.java | Ei Phyu Phyu Thant | 2019-06-11 | 2019-06-11
18 | Empty Pages | Partner | BookingController.java | Htet Eaindray Hlaing | 2019-06-11 | 2019-06-11
19 | Empty Pages | Partner | ClinicController.java | Hmu Pyae Shan | 2019-06-11 | 2019-06-11
20 | Empty Pages | Partner | DoctorController.java | Win Theingi | 2019-06-11 | 2019-06-11
21 | Empty Pages | Partner | PatientController.java | Htet Aung Lin | 2019-06-11 | 2019-06-11 | Complete
22 | Empty Pages | Partner | TimeTableController.java | Zaw Min Lwin | 2019-06-11 | 2019-06-11 | Complete
23
24
25
26
27
28
29
30
31
32
33
34
Formulas:
Date To = [Date From]