## Sheet3
| 2019-06-10 | 2019-06-17 | 2019-06-24 | 2019-07-01 | 2019-07-08 | 2019-07-15 | 2019-07-22 | 2019-07-29
Controller Methods
Empty Pages
Page Design
Controller Methods Implementations
Services Class
Services Methods
Services Methods Implementations
Android
Htet Aung Lin
Person 2
Person 3
Person 4
Person 5
Person 6
Person 7
Zaw Min Lwin
Myat Lin
Issac

## Schedule
ID | Category | Role | Task | Duty | Date From | Date To | Status | Remark
1 | Controller Methods | Anonymous | ClinicController.java | Htet Aung Lin | 2019-06-11 | 2019-06-11
2 | Controller Methods | Anonymous | PublicDoctorController.java | Person 2 | 2019-06-11 | 2019-06-11
3 | Controller Methods | Anonymous | PublicHomeController.java | Zaw Min Lwin | 2019-06-11 | 2019-06-11
4 | Controller Methods | Anonymous | SignUpController.java | Zaw Min Lwin | 2019-06-11 | 2019-06-11
5 | Controller Methods | Member | BookingController.java | Person 3 | 2019-06-11 | 2019-06-11
6 | Controller Methods | Member | FamilyMemberController.java | Person 4 | 2019-06-11 | 2019-06-11
7 | Controller Methods | Partner | MemberBookingController.java | Person 5 | 2019-06-11 | 2019-06-11
8 | Controller Methods | Partner | ClinicController.java | Person 6 | 2019-06-11 | 2019-06-11
9 | Controller Methods | Partner | DoctorController.java | Person 7 | 2019-06-11 | 2019-06-11
10 | Controller Methods | Partner | PatientController.java | Htet Aung Lin | 2019-06-11 | 2019-06-11
11 | Controller Methods | Partner | TimeTableController.java | Zaw Min Lwin | 2019-06-11 | 2019-06-11
12 | Empty Pages | Anonymous | ClinicController.java | Htet Aung Lin | 2019-06-11 | 2019-06-11
13 | Empty Pages | Anonymous | DoctorController.java | Person 2 | 2019-06-11 | 2019-06-11
14 | Empty Pages | Anonymous | HomeController.java | Zaw Min Lwin | 2019-06-11 | 2019-06-11
15 | Empty Pages | Anonymous | SignUpController.java | Zaw Min Lwin | 2019-06-11 | 2019-06-11
16 | Empty Pages | Member | BookingController.java | Person 3 | 2019-06-11 | 2019-06-11
17 | Empty Pages | Member | FamilyMemberController.java | Person 4 | 2019-06-11 | 2019-06-11
18 | Empty Pages | Partner | BookingController.java | Person 5 | 2019-06-11 | 2019-06-11
19 | Empty Pages | Partner | ClinicController.java | Person 6 | 2019-06-11 | 2019-06-11
20 | Empty Pages | Partner | DoctorController.java | Person 7 | 2019-06-11 | 2019-06-11
21 | Empty Pages | Partner | PatientController.java | Htet Aung Lin | 2019-06-11 | 2019-06-11
22 | Empty Pages | Partner | TimeTableController.java | Zaw Min Lwin | 2019-06-11 | 2019-06-11
23
24
25
26
27
28
29
30
31
32
33
34
Formulas:
Date To = [Date From]