## Sheet3
| 2019-06-10 | 2019-06-17 | 2019-06-24 | 2019-07-01 | 2019-07-08 | 2019-07-15 | 2019-07-22 | 2019-07-29
Controller Methods
Empty Pages
Page Design
Controller Methods Implementations
Services Class
Services Methods
Services Methods Implementations
Android
Htet Aung Lin
Chit Thae
Soe Yadanar Tun
Ei Phyu Phyu Thant
Htet Eaindray Hlaing
Hmu Pyae Shan
Win Theingi
Zaw Min Lwin
Myat Lin
Issac

## Schedule
ID | Category | Role | Task | Duty | Date From | Date To | Status | Remark
1 | Controller Methods | Anonymous | ClinicController.java | Htet Aung Lin | 2019-06-11 | 2019-06-11 | Complete
2 | Controller Methods | Anonymous | PublicDoctorController.java | Chit Thae | 2019-06-11 | 2019-06-11 | Complete
3 | Controller Methods | Anonymous | HomeController.java | Zaw Min Lwin | 2019-06-11 | 2019-06-11 | Complete
4 | Controller Methods | Anonymous | SignUpController.java | Zaw Min Lwin | 2019-06-11 | 2019-06-11 | Complete
5 | Controller Methods | Member | MemberBookingController.java | Soe Yadanar Tun | 2019-06-11 | 2019-06-11 | Complete
6 | Controller Methods | Member | FamilyMemberController.java | Ei Phyu Phyu Thant | 2019-06-11 | 2019-06-11 | Complete
7 | Controller Methods | Partner | BookingController.java | Htet Eaindray Hlaing | 2019-06-11 | 2019-06-11 | Complete
8 | Controller Methods | Partner | ClinicController.java | Hmu Pyae Shan | 2019-06-11 | 2019-06-11 | Complete
9 | Controller Methods | Partner | DoctorController.java | Win Theingi | 2019-06-11 | 2019-06-11 | Complete
10 | Controller Methods | Partner | PatientController.java | Htet Aung Lin | 2019-06-11 | 2019-06-11 | Complete
11 | Controller Methods | Partner | TimeTableController.java | Zaw Min Lwin | 2019-06-11 | 2019-06-11 | Complete
12 | Empty Pages | Anonymous | ClinicController.java | Htet Aung Lin | 2019-06-11 | 2019-06-11 | Complete
13 | Empty Pages | Anonymous | PublicDoctorController.java | Chit Thae | 2019-06-11 | 2019-06-11 | Complete
14 | Empty Pages | Anonymous | HomeController.java | Zaw Min Lwin | 2019-06-11 | 2019-06-11 | Complete
15 | Empty Pages | Anonymous | SignUpController.java | Zaw Min Lwin | 2019-06-11 | 2019-06-11 | Complete
16 | Empty Pages | Member | MemberBookingController.java | Soe Yadanar Tun | 2019-06-11 | 2019-06-11 | Complete
17 | Empty Pages | Member | FamilyMemberController.java | Ei Phyu Phyu Thant | 2019-06-11 | 2019-06-11 | Complete
18 | Empty Pages | Partner | BookingController.java | Htet Eaindray Hlaing | 2019-06-11 | 2019-06-11 | Complete
19 | Empty Pages | Partner | ClinicController.java | Hmu Pyae Shan | 2019-06-11 | 2019-06-11 | Complete
20 | Empty Pages | Partner | DoctorController.java | Win Theingi | 2019-06-11 | 2019-06-11 | Complete
21 | Empty Pages | Partner | PatientController.java | Htet Aung Lin | 2019-06-11 | 2019-06-11 | Complete
22 | Empty Pages | Partner | TimeTableController.java | Zaw Min Lwin | 2019-06-11 | 2019-06-11 | Complete
23 | Page Design | Anonymous | clinics.html | Chit Thae | 2019-06-12 | 2019-06-14 | Complete
24 | Page Design | Anonymous | doctor.html | Soe Yadanar Tun | 2019-06-12 | 2019-06-14 | Complete
25 | Page Design | Anonymous | doctors.html | Soe Yadanar Tun | 2019-06-14 | 2019-06-16 | Complete
26 | Page Design | Anonymous | index.html | Htet Aung Lin | 2019-06-11 | 2019-06-12 | Complete
27 | Page Design | Anonymous | login.html | Htet Aung Lin | 2019-06-11 | 2019-06-12 | Complete
28 | Page Design | Anonymous | schedules.html | Ei Phyu Phyu Thant | 2019-06-12 | 2019-06-14 | Complete
29 | Page Design | Anonymous | signup.html | Htet Aung Lin | 2019-06-11 | 2019-06-12 | Complete
30 | Page Design | Member | booking.html | Htet Eaindray Hlaing | 2019-06-12 | 2019-06-14 | Complete
31 | Page Design | Member | bookings.html | Htet Eaindray Hlaing | 2019-06-14 | 2019-06-16 | Complete
32 | Page Design | Member | family-edit.html | Hmu Pyae Shan | 2019-06-12 | 2019-06-14 | Complete
33 | Page Design | Member | family.html | Hmu Pyae Shan | 2019-06-14 | 2019-06-16 | Complete
34 | Page Design | Member | home.html | Htet Aung Lin | 2019-06-13 | 2019-06-15 | Complete
35 | Page Design | Partner | bookings.html | Win Theingi | 2019-06-12 | 2019-06-14 | Complete
36 | Page Design | Partner | clinic-edit.html | Htet Aung Lin | 2019-06-15 | 2019-06-17 | Complete
37 | Page Design | Partner | clinic.html | Htet Aung Lin | 2019-06-17 | 2019-06-19 | Complete
38 | Page Design | Partner | doctor-edit.html | Chit Thae | 2019-06-14 | 2019-06-16 | Complete
39 | Page Design | Partner | doctor.html | Chit Thae | 2019-06-16 | 2019-06-18 | Complete
40 | Page Design | Partner | home.html | Ei Phyu Phyu Thant | 2019-06-14 | 2019-06-16 | Complete
41 | Page Design | Partner | patient.html | Win Theingi | 2019-06-14 | 2019-06-16 | Complete
42 | Page Design | Partner | patients.html | Win Theingi | 2019-06-16 | 2019-06-18 | Complete
43 | Page Design | Partner | schedules.html | Soe Yadanar Tun | 2019-06-16 | 2019-06-18 | Complete
44 | Page Design | Partner | doctors.html | Chit Thae |  |  | Complete
45 | Controller Methods Implementations | Anonymous
46 | Controller Methods Implementations | Anonymous
47 | Controller Methods Implementations | Anonymous
48 | Controller Methods Implementations | Anonymous
49 | Controller Methods Implementations | Member
50 | Controller Methods Implementations | Member
51 | Controller Methods Implementations | Partner
52 | Controller Methods Implementations | Partner
53 | Controller Methods Implementations | Partner
54 | Controller Methods Implementations | Partner
55 | Controller Methods Implementations | Partner
Formulas:
Date To = [Date From]
Date To = [Date From]+2